## Slide 1
Milestone Plan
For Customer development projects

## Slide 2
Save the document Save it in the project folder with the project number in the name like this: ”2133 Milestone Plan.pptx”.
Delete the slides from the template that don’t fit your project E.g. for single-contractor projects only leave the title slide, and the ”Commercial” and ”Single-contractor” slides. Also delete this slide.
Put the project name and number on the title slide Replace ”For Customer development projects” with e.g. ”2133 SGRE Generator Routine Tester”.
Modify flow as necessary Delete or add actions or documents if this project does not quite follow the ordinary flow.
Fill in dates as they are settled This is a living document, dates should be filled in and maintained during the life of the project.
How to use this template

## Slide 3
Commercial

## Slide 4
Commercial
Concepts
Specifications
Quotation & Negotiation
PO
Concepts done
Specifications received
Quote accepted
PO received
Clarification
Commercial
{Date}
{Date}
{Date}
Clarification
Estimated / Confirmed dates :
Quote
Negotiation
Risk management plan

## Slide 5
Single-contractor
GPower -> end customer

## Slide 6
Execution @ GPower
Design
Manufacturing & GPower integration testing
FAT
Kickoff
Manufacturing done
{Date}
{Date}
Execution start
{Date}
FAT accepted
{Date}
Project start
Estimated / Confirmed dates :
Design done
{Date}
Kickoff
Execution
Kickoff meeting
Milestone plan
FAT report
HW design
Interface design
SW design
FAT plan
SAT plan
Alignment
Design review
Alignment
FAT
FAT review
User guide
Installation plan
Maintenance plan
Training plan
Legal use document
CE documentation

## Slide 7
Commisioning @ customer
Packing & Transportation to customer
On-site storage
Run-in
Training
Installation
Arrived
{Date}
Ready for installation
{Date}
Installed
{Date}
Ready for training
{Date}
Training complete
{Date}
Delivery
Installation
Training
Estimated / Confirmed dates :
Send received notice
Alignment
Alignment
Training

## Slide 8
Handover @ customer
SAT
In warranty period
Out of warranty period
Handover complete
{Date}
Out of warranty
{Date}
Handover
In warranty
Out of warranty
Estimated / Confirmed dates :
As-built documentation
SAT report
Warranty certificate
SAT review
Followup
Send out of warranty notice
Followup
SAT

## Slide 9
Multi-contractor: GPower is main contractor
Sub-contractor -> GPower -> end customer

## Slide 10
Execution @ GPower
Design
Manufacturing & GPower integration testing
FAT
Kickoff
Manufacturing done
{Date}
{Date}
Execution start
{Date}
FAT accepted
{Date}
Project start
Estimated / Confirmed dates :
Design done
{Date}
Kickoff
Execution
Kickoff meeting
Alignment
Design review
Alignment
FAT
FAT review
Commissioning planning
Integration planning
Kickoff meeting
Alignment
Alignment
Milestone plan
FAT report
FAT plan
SAT plan
SIT plan
Design review
HW design
Interface design
SW design
User guide
Installation plan
Maintenance plan
Training plan
Legal use document
CE documentation

## Slide 11
Integration @ GPower
Packing & Transportation to GPower
On-site storage
Run-in
SIT
Installation
Arrived
{Date}
Ready for installation
{Date}
Installed
{Date}
Ready for SIT
{Date}
SIT accepted
{Date}
Delivery
Systems integration
Estimated / Confirmed dates :
SIT report
SIT review
SIT
Send received notice
Installation support
Run-in support
SIT review

## Slide 12
Commisioning @ customer
Packing & Transportation to customer
On-site storage
Run-in
Training
Installation
Arrived
{Date}
Ready for installation
{Date}
Installed
{Date}
Ready for training
{Date}
Training complete
{Date}
Delivery
Installation
Training
Estimated / Confirmed dates :
Send received notice
Alignment
Alignment
Training
Training support
Installation support
Run-in support

## Slide 13
Handover @ customer
SAT
In warranty period
Out of warranty period
Handover complete
{Date}
Out of warranty
{Date}
Handover
In warranty
Out of warranty
Estimated / Confirmed dates :
SAT review
Followup
Send out of warranty notice
Followup
SAT
SAT support
As-built documentation
SAT report
Warranty certificate
SAT review
Followup

## Slide 14
Multi-contractor: GPower is sub-contractor
GPower -> contractor -> end customer

## Slide 15
Execution @ GPower
Design
Manufacturing & GPower integration testing
FAT
Kickoff
Manufacturing done
{Date}
{Date}
Execution start
{Date}
FAT accepted
{Date}
Project start
Estimated / Confirmed dates :
Design done
{Date}
Kickoff
Execution
Kickoff meeting
Alignment
Design review
Alignment
FAT
FAT review
Commissioning planning
Integration planning
Kickoff meeting
Alignment
Alignment
Design review
Milestone plan
FAT report
FAT plan
SAT plan
SIT plan
HW design
Interface design
SW design
User guide
Installation plan
Maintenance plan
Training plan
Legal use document

## Slide 16
Integration @ contractor
Packing & Transportation to contractor
On-site storage
Run-in
SIT
Installation
Arrived
{Date}
Ready for installation
{Date}
Installed
{Date}
Ready for SIT
{Date}
SIT accepted
{Date}
Delivery
Systems integration
Estimated / Confirmed dates :
SIT report
SIT review
SIT
Send received notice
Installation support
Run-in support
SIT review

## Slide 17
Commisioning @ customer
Packing & Transportation to customer
On-site storage
Run-in
Training
Installation
Arrived
{Date}
Ready for installation
{Date}
Installed
{Date}
Ready for training
{Date}
Training complete
{Date}
Delivery
Installation
Training
Estimated / Confirmed dates :
Send received notice
Alignment
Alignment
Training
Training support
Installation support
Run-in support

## Slide 18
Handover @ customer
SAT
In warranty period
Out of warranty period
Handover complete
{Date}
Out of warranty
{Date}
Handover
In warranty
Out of warranty
Estimated / Confirmed dates :
Send out of warranty notice
As-built documentation
SAT report
Warranty certificate
SAT review
Followup
Followup
SAT
SAT support
SAT review
Followup